## final overview
July 9th final summary of cruise activities
file VERTIGO final cruise activities.xls
Basic plan includes survey of larger area as we arrive on site near HOT (50km scales) within which we would
cluster Siegels drifters
At this central 5x5 grid, we would focus most of the process study and deployment of all devices. After 2-3 days, from the
mean velocity profiles, we'll know more about the particle source region and would readjust sampling appropriately. Initial
calculations suggest this larger scale might take us 10-20 km from central point
We need 3-5 days for adequate material from traps, so hope within 3 week cruise, at best, to have 2 deployments
of NBST & other gear. An example of this plan has been revised here
Julian Day | 172_173 | 173_174 | 174_175 | 175_176 | 176_177 | 177_178 | 178_179 | 179_180 | 180_181 | 181_182 | 182_183 | 183_184 | 184_185 | 185_186 | 186_187 | 187_188 | 188_189 | 189_190 | 190_191 | 191_192 | 192_193 | 193_194
VERTIGO ship plans- June 2004 |  |  | particle collections | day 0 | day 1 | day 2 | day 3 | day 4 | day 5 | Survey | Survey | Survey | day 0 | 1 | 2 | 3 | 4 | 5 | 6
| 2004-06-20 | 2004-06-21 | 2004-06-22 | 2004-06-23 | 2004-06-24 | 2004-06-25 | 2004-06-26 | 2004-06-27 | 2004-06-28 | 2004-06-29 | 2004-06-30 | 2004-07-01 | 2004-07-02 | 2004-07-03 | 2004-07-04 | 2004-07-05 | 2004-07-06 | 2004-07-07 | 2004-07-08 | 2004-07-09 | 2004-07-10 | 2004-07-11
hours | day 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
0 |  | SS#1 CTD 2-18 | SS#1 CTD 2-18 | Trull trap in- 300 | Survey CTD #24 & drifters | MOCNESS | MULVFS | NBST 300 out | MOCNESS | CTD # 40-44 | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | Survey CTD #77 & drifters | MOCNESS | MULVFS | SS | CTD #94 | MOCNESS | SS | steam to port
2 |  | SS#1 CTD 2-18 | SS#1 CTD 2-18 | Launch Clap 150 | Survey CTD #25 & drifters | SS | MULVFS | NBST 300 out | NBST 500 out | CTD # 40-44 | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | Survey CTD #78 & drifters | SS | MULVFS | CTD #89 | bio cast-tow | MOCNESS | SS | steam to port
4 |  | SS#1 CTD 2-18 | recover 12hr NBST | STD bio cast- CTD #19 & Th CTD20 | 1000m CTD #26 | CTD biocast #27 (shallow) | MULVFS | CTD #32 | NBST 500 out | STD bio cast- CTD#45 | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | Survey CTD & drifters | 1000m CTD #81 | MAX CTD #83 | Deep plankton tow | STD bio cast- CTD#95 | SS | MAX CTD #99 | steam to port
6 | depart 0800 | SS#1 CTD 2-18 | SS#1 CTD 2-18 | Launch Clap 300 | Launch-optical trap | CTD biocast #28 (deep) | MULVFS | STD bio cast- CTD#33 | NBST 500 out | Launch-optical trap | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | STD bio cast- CTD#79 | SS | MAX CTD #84 | CTD N2 fix | CTD #96 | SS | MAX CTD #100 | steam to port
8 |  | SS#1 CTD 2-18 | SS#1 CTD 2-18 | Launch Clap 500 | Launch-optical trap | MULVFS | NBST 150 out | Clap 300 out | Clap 500 out | Trull trap out | CTD # 46-66 | Trull trap in- 300 | CTD # 67-73 | CTD #80 | MULVFS | CTD #85-88 | Deep CTD #90- 3000m Ba/Th | SS | MOCNESS | 210Pb LV CTD #101 | Arrive Honolulu 0900
10 |  | recover 12 hr NBST | plankton net test- Silver/Tanner | Launch NBST 150 | MOCNESS | MULVFS | NBST 150 out | CTD # 34-39 | MOCNESS | bio cast-tow | CTD # 46-66 | CTD # 67-73 | CTD # 67-73 | MOCNESS | MULVFS | CTD #85-88 | Deep CTD #90- 3000m Ba/Th | Shallow MULVFS | MOCNESS | N2 fix CTD #102 | Arrival 1 day early
12 |  | SS#1 CTD 2-18 | MOCNESS test | Launch NBST 300 | MOCNESS | MULVFS | NBST 150 out | CTD # 34-39 | MOCNESS | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | Launch 150 Clap & NBST | MOCNESS | MULVFS | CTD #85-88 | CTD #91-93 | Shallow MULVFS | Trull trap out | Depart for Honolulu
14 |  | SS#1 CTD 2-18 | MULVFS test | Launch NBST 500 | Launch respirometer | MULVFS | Clap 150 out | CTD # 34-39 | CTD # 40-44 | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | Launch 300 Clap & NBST | bio cast-tow | MULVFS | CTD #85-88 | CTD #91-93 | Shallow MULVFS | Trull trap out | steam to port
16 |  | deploy 12hr NBST test | MULVFS test | Survey CTD #21 & drifters | Go-Flo casts | Deep CTD 29- 3000m Ba/Th | Clap 150 out | CTD # 34-39 | CTD # 40-44 | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | Launch 500 Clap & NBST | Go-Flo casts | bio cast-tow | CTD #85-88 | Optical trap IN | SS | CTD #97 | steam to port
18 |  | SS#1 CTD 2-18 | SS#1 CTD 2-18 | Survey & drifters | Go-Flo casts | Deep CTD 29- 3000m Ba/Th | CTD #30 & 31 | CTD # 34-39 | CTD # 40-44 | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | Launch 500 Clap & NBST | Go-Flo casts | CTD #82- 500m high Res | Clap 150 out | Clap 300 out | Clap 500 out | Optical trap out | steam to port
20 | deploy 12hr NBST test | optical trap test | Launch 1 Siegel drifter | Survey CTD #22 & drifters | Launch C explorer | MULVFS | optical trap out | CTD # 34-39 | CTD # 40-44 | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | Launch-optical trap | SS | MULVFS | NBST 150 out | NBST 300 out | NBST 500 out | Optical trap out | steam to port
22 | SS#1 CTD 2-18 | SS#1 CTD 2-18 | Trull trap in- 300 | Survey CTD #23 & drifters | MOCNESS | MULVFS | bio cast-tow | MOCNESS | CTD # 40-44 | CTD # 46-66 | CTD # 46-66 | CTD # 67-73 | Survey CTD #74-76 & drifters | MOCNESS | MULVFS | optical trap out | MOCNESS Dip/clean | NBST 500 out | CTD #98 | steam to port
[12 empty] | SS |  |  | Clap 150 out
| day 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | day 10 to 16 | days 17-23 | SS |  |  | Clap 150 out
hours | day 1: steaming & survey; 2: survey & start NBST |  |  | steam home
0 |  | A. site survey cast | B. Launch ARGOS floats & CTD. | C. Central grid & launch in situ | F. Pump cast | F. Pump cast | H. Pick up & casts | H. Pick up & casts | G. Physical cast | F. Pump cast
2 |  | A. site survey cast | B. Launch ARGOS floats & CTD. | C. Central grid & launch in situ | G. Physical cast | G. Physical cast | H. Pick up & casts | H. Pick up & casts | G. Physical cast | G. Physical cast
4 |  | A. site survey cast | C. Central grid & launch in situ | D. Biology cast- CTD | D. Biology cast- CTD | D. Biology cast- CTD | H. Pick up & casts | H. Pick up & casts | D. Biology cast- CTD | AND REPEAT DAY 3-9 | AND REPEAT DAY 3-9
6 | depart | A. site survey cast | C. Central grid & launch in situ | E. Biology cast- plankton | E. Biology cast- plankton | E. Biology cast- plankton | H. Pick up & casts | H. Pick up & casts | E. Biology cast- plankton
8 | steam to HOT | A. site survey cast | C. Central grid & launch in situ | F. Pump cast | F. Pump cast | G. Physical cast | H. Pick up & casts | H. Pick up & casts | F. Pump cast
10 |  | A. site survey cast | C. Central grid & launch in situ | F. Pump cast | F. Pump cast | G. Physical cast | H. Pick up & casts | H. Pick up & casts | F. Pump cast
12 |  | A. site survey cast | C. Central grid & launch in situ | F. Pump cast | F. Pump cast | G. Physical cast | H. Pick up & casts | H. Pick up & casts | F. Pump cast
14 |  | A. site survey cast | C. Central grid & launch in situ | G. Physical cast | G. Physical cast | G. Physical cast | H. Pick up & casts | G. Physical cast | G. Physical cast
16 |  | A. site survey cast | C. Central grid & launch in situ | G. Physical cast | G. Physical cast | G. Physical cast | H. Pick up & casts | G. Physical cast | G. Physical cast
18 |  | A. site survey cast | C. Central grid & launch in situ | D. Biology cast- CTD | D. Biology cast- CTD | G. Physical cast | H. Pick up & casts | G. Physical cast | D. Biology cast- CTD
20 | A. site survey cast | B. Launch ARGOS floats & CTD. | C. Central grid & launch in situ | E. Biology cast- plankton | E. Biology cast- plankton | E. Biology cast- plankton | H. Pick up & casts | G. Physical cast | E. Biology cast- plankton
22 | A. site survey cast | B. Launch ARGOS floats & CTD. | C. Central grid & launch in situ | F. Pump cast | F. Pump cast | G. Physical cast | H. Pick up & casts | G. Physical cast | F. Pump cast
24 | A. site survey cast | B. Launch ARGOS floats & CTD. | C. Central grid & launch in situ | F. Pump cast | F. Pump cast | G. Physical cast | H. Pick up & casts | G. Physical cast | F. Pump cast
Event type | day 1: SS = Site Survey cast= CTD/Rosette w/trans, flu, sensors, option to trip bottles mostly 0-500m
sampling scales- within 20-50km scales & coming in to station and during mid-cruise, large 100km scales for "butterfly" survey
Launch surface drifters (n=5) over 15x15km grid
include CTD at grid points; 1 hr steam & 1 hr CTD at each point; floats will not be retrieved
Central 5x5 km grid & launch main in-situ gear
includes NBST (n=7), Optical sediment trap; C explorer float ( Bishop), Drogued Clap traps (n=3); Repirometer array (n=1); Trull trap array
Includes CTD work (and other sampling?) at n=5 grid points
STD biology cast- CTD (New Prod, 234Th & others- dawn; bottles tripped for ancillary nutrients, Chl, pigments, etc)
biology net tow- many short tows taken are not on this summary- plankton net tow for microscope work and live experiments- Silver and Steinberg
F. Pump cast (day and night pairs) assume 8 hours each
Deep-CTD- Ba/Th is cast dedicated to particulate Ba for Dehairs (focus on 100-1500m sampling) with 2-4 bottles tripped at 3000m for 234Th calibration
CTD- 500m high Res is Trull led CTD w/24 depths across pycnocline to 500m
Go-Flo casts for trace metals- Lamborg
Pick-up gear out of water (optional CTD survey casts at site of pick up)
MOCNESS- 4 hour cast
210Pb LV CTD cast- need to trip 20 bottles to get 10 samples for 210Pb profile- 20 L each